## Training Templates
SlNo | Trainee | Technology | Tech Buddy | Mentor | Start Date | End Date | Status/Comment | Assessment Review/ Final Feed Back
1 | Krishna Uttej/ COFEE Team | HTML | Priyadharshini | Venkata Kamparaju | 2020-07-31 | 2020-08-28 | Completed
2 |  | CSS |  |  |  |  | Completed
3 |  | Javascript |  |  |  |  | Completed
4 |  | ReactJS |  |  |  |  | Completed
5 |  | Java | Abhishek Kumar |  | 2020-08-31 | 2020-09-30 | Completed
6 |  | Spring |  |  |  |  | Completed
7 |  | SpringBoot |  |  |  |  | Completed
8 |  | Microservices |  |  |  |  | Completed
9 |  | Hibernate |  |  | 2020-09-22 | 2020-02-11 | Completed
10 |  | Postgres |  |  |  |  | Completed
11 |  | SQL |  |  |  |  | Completed
12 |  | Project |  |  | 2020-11-02

## Java (2) (hidden)
S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | Actual Completion Time(in hours) | Reviewer Name | Review Comments | Note(If any)
1 | An Overview of Java, JDK, JVM, JRE | Nandhini |  |  | 1
2 | Data Types, Variables and Arrays |  |  |  | 1
3 | Operators
4 | Control Statements |  |  |  | 1
5 | Class, Packages and Interfaces | Christine |  |  | 1
6 | Access specifiers and access Modifiers
7 | Oops Concepts | Christine |  |  | 1
8 | String Handling - Only String | Digant |  |  | 1
9 | Exception Handling | Digant |  |  | 1
10 | Multithreaded Programming |  |  |  | 1
11 | Enumerations, Auto-boxing and Annotations (Meta-data) |  |  |  | 1
12 | I / O |  |  |  | 1
13 | Generics | Sundar |  |  | 1
15 | String Handling - Builder and Buffer | Nandhini |  |  | 1
17 | Exploring java.lang |  |  |  | 1
| The Collections Framework - Part 1 | Seva Priya
18 | The Collections Framework - Part 1 | Seva Priya |  |  | 1
21 | Exploring NIO |  |  |  | 1
22 | Text, Date | Digant |  |  | 1
23 | The Co-currency Utilities |  |  |  | 1
24 | The Stream API |  |  |  | 1
25 | Regular Expressions and Other Packages |  |  |  | 1
26 | Final Application |  |  |  | 1
Java 8 programming Features
| Lambda | Seva Priya
| Funcational Interface | Madhu
| String Joiner | Madhu
| Optional | Madhu
| Method Reference | Madhu

## Html
What Is ?
Understanding Tags |  |  | Start Date | 2020-03-08 | End Date | 20/08/2020
Understanding Cascading Style Sheets
Why Learn in Notepad? | S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | Assessment Status | Reviewer Name | Review Comments | Note(If any)
Choosing an Version | 1 | Introduction to HTML | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done | Deep diving through w3schools to apply for the concepts for POC
Why Code in 5? | 2 | Elements | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Minimum System Requirements | 3 | Attributes | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Setting Up the Document Structure | 4 | Headings | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Specifying the Document Type | 5 | Paragraphs | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Creating the , Head, and Body Sections | 6 | Styles | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Creating Paragraphs and Line Breaks | 7 | Formatting | self | 2020-03-08 |  | 0.5 | Done | Venkat | Done
Specifying a Page Title and Metatags | 8 | Quotations | self | 2020-04-08 |  | 0.5 | Done | Venkat | Done
Publishing a File to a Server | 9 | Comments | self | 2020-04-08 |  | 0.5 | Done | Venkat | Done
Formatting Text by Using Tags | 10 | Colors | self | 2020-04-08 |  | 0.5 | Done | Venkat | Done
Creating Headings | 11 | CSS | self | 2020-04-08 |  | 1 | Done | Venkat | Done
Applying Bold and Italic Formatting | 12 | Links | self | 2020-04-08 |  | 0.5 | Done | Venkat | Done
Using Monospace and Preformatted Text | 13 | Images | self | 2020-04-08 |  | 0.5 | Done | Venkat | Done
Formatting a Block Quotation | 14 | Tables | self | 2020-06-08 |  | 1 | Done | Venkat | Done
Using Lists and Backgrounds | 15 | Lists | self | 2020-07-08 |  | 1.5 | Done | Venkat | Done
Nesting Lists | 16 | Blocks | Self | 2020-07-08 |  | 1 | Done | Venkat | Done
Changing the Bullet or Number Character | 17 | Classes | Self | 2020-07-08 |  | 1 | Done | Venkat | Done
Specifying the Start of a Numbered List | 18 | Iframes | self | 2020-10-08 |  | 1 | Done | Venkat | Done
Creating Definition Lists | 19 | JavaScript | self | 2020-10-08 |  | 1 | Done | Venkat | Done
Inserting Special Characters | 20 | File Paths | self | 2020-11-08 |  | 1 | Done | Venkat | Done
Inserting Horizontal Lines | 21 | Layout | self | 2020-11-08 |  | 1 | Done | Venkat | Done
Choosing Background and Foreground Colors | 22 | Responsive | self | 2020-11-08 |  | 1 | Done | Venkat | Done
Specifying Colors | 23 | Computercode | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
Applying a Background Color | 24 | Entities | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
Creating Hyperlinks and Anchors | 25 | Symbols | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
Hyperlinking to a Web Page | 26 | Charset | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
Using Partial Paths and Filenames | 27 | URL Encode | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
Using Relative and Absolute Paths | 28 | XHTML | self | 08-14-2025 |  | 0.25 | Done | Venkat | Done
Introduction to Style Sheets | 29 | Forms | self | 08-14-2020 |  | 0.5 | Done | Venkat | Done
Understanding Styles | 30 | Form Elements | self | 08-14-2020 |  | 1 | Done | Venkat | Done
Constructing Style Rules | 31 | Input Types | self | 08-14-2020 |  | 1 | Done | Venkat | Done
Creating Styles for Nested Tags | 32 | Input Attributes | self | 08-14-2020 |  | 1 | Done | Venkat | Done
Creating Classes and IDs for Applying Styles | 33 | HTML5 Elements | self | 08-14-2020 |  | 1 | Done | Venkat | Done
Applying Styles to Hyperlinks | 34 | Canvas | self | 08-18-2020 |  | 0.5 | Done | Venkat | Done
Formatting Text by Using Style Sheets | 35 | SVG | self | 08-18-2020 |  | 0.5 | Done | Venkat | Done
Specifying a Font Family | 36 | Media | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
Specifying a Font Size and Color | 37 | HTML Video | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
Applying Bold and Italics | 38 | HTML Audio | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
Applying Strikethrough and Underlining | 39 | HTML Plug-ins | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
Creating Inline Spans | 41 | Geolocation | self | 08-19-2020 |  | 0.5 | Done | Venkat | Done
Adjusting Spacing Between Letters | 42 | Using Drag/Drop feature | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
Adding Figure Captions | 43 | HTML Web Storage | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
Creating Navigational Aids | 44 | Web Workers | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
Planning Your Site’s Organization | 45 | SSE | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
Creating a Text-Based Navigation Bar
Creating a Graphical Navigation Bar
Creating an Image Map
Redirecting to Another URL
Creating Division-Based Layouts
Understanding 5 Semantic Tags
Beginning to Think in Divisions
Creating Divisions
Creating an 5 Semantic Layout
Positioning Divisions
Floating a Division to the Right or Left
Positioning a Division on the Page
Formatting Divisions
Creating Tables
Creating a Simple Table
Specifying the Size of a Table
Specifying the Width of a Column
Merging Table Cells
Using Tables for Page Layout
Formatting Tables
Applying Table Borders
Applying Borders by Using Attributes
Applying Borders by Using Styles
Applying Background and Foreground Fills
Changing Cell Padding, Spacing, and Alignment
Setting Cell Padding
Setting Cell Spacing
Setting Horizontal and Vertical Alignment
Creating User Forms
Creating a Basic Form
Creating a Text Box
Special Field Types for E-Mail and Web Addresses
Creating a Text Area
Creating a Submit or Clear Button
Adding Default or Placeholder Text
Creating Check Boxes and Option Buttons
Creating Lists
Additional Input Types in 5
Understanding CGI and Other Advanced Tools
5 Incorporating Sound and Video
What’s New with Audio and Video in 5?
Multimedia Basics
Multimedia Formats and Containers
Codecs: Decoding the Video and Audio
Which Format to Choose?
File Size and Quality
Encoding Video
Embedding Video Clips
Introducing the <video> Tag
The <embed> Tag: Your Fallback Plan
Placing a Video Clip on a Web Page
Incorporating Audio on a Web Page
Playing Audio with the <audio> Tag
Playing Audio in Older Browsers
Placing an Audio Clip on a Web Page
Including JavaScript and External Content
Introducing the Canvas
JavaScript, Briefly
Including JavaScript on Your Web Page
Your First JavaScript Web Page
JavaScript Events and jQuery
Obtaining jQuery
Getting Ready for jQuery
Selecting Elements with jQuery
Calling Functions with JavaScript
Responding to Events with jQuery and JavaScript
Using the 5 <canvas> Tag
Including External Content in Web Pages
Designing for Usability
Understanding Usability
Planning for Usability
Sketching the Site Organization
Designing a Consistent Page Template
Designing the Content of Individual Pages
Performing Usability Testing
Designing for Accessibility
Guideline 1: Provide Equivalent Alternatives to Auditory and Visual Content
Guideline 2: Don’t Rely on Color Alone
Guideline 3: Use Markup and Style Sheets, and Do So Properly
Guideline 4: Clarify Natural Language Usage
Guideline 5: Create Tables that Transform Gracefully
Guideline 6: Ensure that Pages Featuring New Technologies Transform Gracefully
Guideline 7: Ensure User Control of Time-Sensitive Content Changes
Guideline 8: Ensure Direct Accessibility of Embedded User Interfaces
Guideline 9: Design for Device Independence
Guideline 10: Use Interim Solutions
Guideline 11: Use W3C Technologies and Guidelines

## CSS
Training Start Date
Training End Date
S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | Assesment Status | Reviewer Name | Review Comments | Note(If any)
1 | Introduction to CSS | Jeelani |  | implement different ways of CSS styling in same page | 3(08-11-2020) | Done | venkat | Done
3 | Units in CSS | Jeelani |  | modify various HTML elements using different CSS units | (08-13-2020) | Done | venkat | Done
6 | DOM Manipulation | Jeelani |  | Implement the box pattern using CSS
8 | Links, overflow | Jeelani |  | Implementing FLEX to create the layout given
11 | Padding, Margins | Jeelani |  | Implementing GRID to create the layout given
15 | Position, z-index | Jeelani |  | CREATE A GAME USING CSS AND JS
19 | RWD with media queries | Jeelani |  | develop a responsive layout for mobile, tablet and desktop with a single page | (08-17-2020) | Done | Venkat | Done
20 | Bootstrap | Jeelani |  | develop a single responsive page using bootstrap classes | (08-17-2020) | Done | Venkat | Done

## JS
|  |  | startDate | 2020-07-08
|  |  | EndDate | 20/8/2020
S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | ASSESSMENT STATUS | Reviewer Name | Review Comments | Note(If any)
1 | JS HOME | Self | 2020-07-08 |  | 1 | Done | Venkat | Done | Deep diving through w3schools to apply for the concepts for POC
2 | JS Introduction | Self | 2020-07-08 |  | 1 | Done | Venkat | Done
3 | JS Where To | Self | 2020-07-08 |  | 1 | Done | Venkat | Done
4 | JS Output | Self | 2020-07-08 |  | 1 | Done | Venkat | Done
5 | JS Statements | self | 2020-10-08 |  | 1 | Done | Venkat | Done
6 | JS Syntax | self | 2020-10-08 |  | 1 | Done | Venkat | Done
7 | JS Comments | self | 2020-10-08 |  | 0.5 | Done | Venkat | Done
8 | JS Variables | self | 2020-10-08 |  | 0.5 | Done | Venkat | Done
9 | JS Operators | self | 2020-10-08 |  | 1 | Done | Venkat | Done
10 | JS Arithmetic | self | 2020-10-08 |  | 0.5 | Done | Venkat | Done
11 | JS Assignment | self | 2020-11-08 |  | 0.5 | Done | Venkat | Done
12 | JS Data Types | self | 2020-11-08 |  | 1 | Done | Venkat | Done
13 | JS Functions | self | 2020-11-08 |  | 1 | Done | Venkat | Done
14 | JS Objects | self | 2020-12-08 |  | 1 | Done | Venkat | Done
15 | JS Events | self | 2020-12-08 |  | 0.5 | Done | Venkat | Done
16 | JS Strings | self | 2020-12-08 |  | 0.5 | Done | Venkat | Done
17 | JS String Methods | self | 2020-12-08 |  | 0.25 | Done | Venkat | Done
18 | JS Numbers | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
19 | JS Number Methods | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
20 | JS Arrays | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
21 | JS Array Methods | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
22 | JS Array Sort | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
23 | JS Array Iteration | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
24 | JS Dates | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
25 | JS Date Formats | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
26 | JS Date Get Methods | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
27 | JS Date Set Methods | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
28 | JS Math | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
29 | JS Random | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
30 | JS Booleans | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
31 | JS Comparisons | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
32 | JS Conditions | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
33 | JS Switch | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
34 | JS Loop For | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
35 | JS Loop While | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
36 | JS Break | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
37 | JS Type Conversion | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
38 | JS Bitwise | self | 08-13-2020 |  | 0.25 | Done | Venkat | Done
39 | JS RegExp | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
40 | JS Errors | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
41 | JS Scope | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
42 | JS Hoisting | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
43 | JS Strict Mode | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
44 | JS this Keyword | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
45 | JS Let | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
46 | JS Const | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
47 | JS Arrow Function | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
48 | JS Classes | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
49 | JS Debugging | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
50 | JS Style Guide | self | 08-14-2020 |  | 0.25 | Done | Venkat | Done
51 | JS Best Practices | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
52 | JS Mistakes | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
53 | JS Performance | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
54 | JS Reserved Words | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
55 | JS Versions | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
56 | JS Version ES5 | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
57 | JS Version ES6 | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
58 | JS JSON | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
59 | JS Forms | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
60 | Forms API | self | 08-17-2020 |  | 0.5 | Done | Venkat | Done
61 | Objects | self | 08-18-2020 |  | 0.5 | Done | Venkat | Done
68 | Functions | self | 08-18-2020 |  | 0.5 | Done | Venkat | Done
74 | DOM Intro | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
75 | DOM Methods | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
76 | DOM Document | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
77 | DOM Elements | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
78 | DOM HTML | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
79 | DOM CSS | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
80 | DOM Animations | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
81 | DOM Events | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
82 | DOM Event Listener | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
83 | DOM Navigation | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
84 | DOM Nodes | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
85 | DOM Collections | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
86 | DOM Node Lists | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
87 | JS Window | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
88 | JS Screen | self | 08-19-2020 |  | 0.25 | Done | Venkat | Done
89 | JS Location | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
90 | JS History | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
91 | JS Navigator | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
92 | JS Popup Alert | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
93 | JS Timing | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
94 | JS Cookies | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
95 | AJAX Intro | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
96 | AJAX XMLHttp | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
97 | AJAX Request | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
98 | AJAX Response | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
99 | AJAX XML File | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
100 | AJAX PHP | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
101 | AJAX ASP | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
102 | AJAX Database | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
103 | AJAX Applications | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
104 | AJAX Examples | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done
105 | JSON | self | 08-20-2020 |  | 0.25 | Done | Venkat | Done

## React
S.NO | Topic | HOURS | Start Date | End Date | Questions | Comments | Note(If any)
1 | React Introduction and installation | 1 | 2020-03-08 | 2020-03-08 |  | Done | Source(Youtube-Codevolution)
2 | Hello World | 1 | 2020-04-08 | 2020-04-08 |  | Done | Source(Youtube-Codevolution)
3 | Introducing JSX | 1 | 2020-04-08 | 2020-04-08 |  | Done | Source(Youtube-Codevolution)
4 | Rendering Elements | 1 | 2020-05-08 | 2020-05-08 |  | Done | Source(Youtube-Codevolution)
5 | Components and Props | 1 | 2020-05-08 | 2020-05-08 |  | Done | Source(Youtube-Codevolution)
6 | State and Lifecycle | 1 | 2020-10-08 | 2020-10-08 |  | Done | Source(Youtube-Codevolution)
7 | Handling Events | 1 | 2020-11-08 | 2020-11-08 |  | Done | Source(Youtube-Codevolution)
8 | Conditional Rendering | 1 | 2020-12-08 | 2020-12-08 |  | Done | Source(Youtube-Codevolution)
9 | Lists and Keys | 1 | 2020-12-08 | 2020-12-08 |  | Done | Source(Youtube-Codevolution)
10 | Forms | 1 | 2020-12-08 | 2020-12-08 |  | Done | Souce(Youtube-Codevolution)
11 | Lifting State Up | 1 | 08-21-2020 | 08-21-2020 |  | Done | react documentation
12 | Composition vs Inheritance | 1 | 08-28-2020 | 08-28-2020 |  | Done | react documentation
13 | Thinking In React | 1 | 08-28-2020 | 08-28-2020 |  | Done | react documentation
14 | Context | 1 | 08-18-2020 | 08-18-2020 |  | Done | react documentation
15 | React Without ES6 | 1 | 08-21-2020 | 08-21-2020 |  | Done | Souce(Youtube-Codevolution)
16 | Lifecycle methods | 1 | 08-18-2020 | 08-18-2020 |  | Done | Source(Youtube-Codevolution)
17 | Hooks | 1 | 08-18-2020 | 08-18-2020 |  | Done | Source(Youtube-Codevolution)
18 | Redux | 1 | 08-19-2020 | 08-19-2020 |  | Done | Source(Youtube-Codevolution)
19 | react-redux | 2 | 08-19-2020 | 08-19-2020 |  | Done | Source(Youtube-Codevolution)
20 | Redux-thunk | 1 | 08-28-2020 | 08-28-2020 |  | Done | Source(Youtube-Codevolution)
21 | React-router | 1 | 08-18-2020 | 08-18-2020 |  | Done | source(youtube-Dev Ed)

## Java
|  | Training Start Date | 2020-08-05
|  | Training End Date | September 11 ,2020
S.NO | Topic | Estimated Hour | Week | Estimated Start Date | Estimated End Date | Acutal End Date | Comments | Note(If any)
1 | Overview of Java | 1 |  | 2020-05-08 | 2020-05-08 | 2020-05-08
2 | Data Types, Variables,and Arrays | 1 |  | 2020-05-08 | 2020-05-08 | 2020-05-08
3 | Operators | 1 |  | 2020-05-08 | 2020-05-08 | 2020-05-08
4 | Control Statements | 1 |  | 2020-06-08 | 2020-06-08 | 2020-06-08
5 | Methods and Classes | 1 |  | 2020-06-08 | 2020-06-08 | 2020-06-08
6 | Inheritance | 1 |  | 25/8/2020 | 25/8/2020 | 25/8/2020
7 | Package and Interfaces | 0.5 |  | 25/8/2020 | 25/8/2020 | 25/8/2020
8 | Exceptional Handling | 1 |  | 25/8/2020 | 25/8/2020 | 25/8/2020 |  |  | 2019-11-10
9 | Multithreaded Programming | 1.5 |  | 2020-01-09 | 2020-01-09 | 2020-01-09
10 | Enumeration,Autoboxing and Annotations | 1 |  | 2020-02-09 | 2020-02-09 | 2020-02-09
11 | Generics | 1 |  | 27/8/2020 | 27/8/2020 | 27/8/2020
12 | String Handling | 1 |  | 26/8/2020 | 26/8/2020 | 26/8/2020
13 | Collection Framework part1 | 1 |  | 26/8/2020 | 26/8/2020 | 26/8/2020
| Collection Framework part2 | 1 |  | 27/8/2020 | 27/8/2020 | 27/8/2020
14 | Exploring java.lang | 0.5 |  | 2020-02-09 | 2020-02-09 | 2020-02-09
15 | Exploring java.io | 0.5 |  | 2020-02-09 | 2020-02-09 | 2020-02-09
16 | Exploring NIO | 0.5 |  | 2020-02-09 | 2020-02-09 | 2020-02-09
17 | I/O Applets | 1 |  | 2020-02-09 | 2020-02-09 | 2020-02-09
18 | Java8 Features-Lambda Expressions | 0.5 |  | 2020-07-09 | 2020-07-09 | 2020-07-09
19 | Java8 Features-Method References | 0.5 |  | 2020-08-09 | 2020-08-09 | 2020-08-09
20 | Java8 Features-Functional Interfaces | 0.5 |  | 2020-07-09 | 2020-07-09 | 2020-07-09
21 | Java8 Features-Stream | 0.5 |  | 2020-08-09 | 2020-08-09 | 2020-08-09
22 | Java8 Features-Default Methods | 0.5 |  | 2020-07-09 | 2020-07-09 | 2020-07-09
23 | Java8 Features-forEach loop | 0.5 |  | 2020-07-09 | 2020-07-09 | 2020-07-09
24 | Java8 Features-Collectors | 0.5 |  | 2020-08-09 | 2020-08-09 | 2020-08-09
25 | Java8 Features-StringJoiner | 1 |  | 2020-09-09 | 2020-09-09 | 2020-09-09
26 | Java8 Features-Optional Class and Javascript Nashorn | 1 |  | 2020-09-09 | 2020-09-09 | 2020-09-09
27 | Java8 Features-Parallel Array Sorting and Type Inference | 1 |  | 2020-10-09 | 2020-10-09 | 2020-10-09
28 | Java8 Features-Method Parameter Reflection | 1 |  | 2020-11-09 | 2020-11-09 | 2020-11-09
29 | Java8 Features-Type Annotations and JDBC Improvements | 0.5 |  | 2020-11-09 | 2020-11-09 | 2020-11-09

## Spring
|  |  | Training Start Date | 2020-08-24
Training End Date
S.NO | Topic | week | Hours Estimatted | start date | end date | status | Questions | comments | Note(If any)
1 | "Simplifying Java development " |  | 1 | 2020-08-24 | 2020-08-24
2 | Containing your beans |  | 1 | 2020-08-24 | 2020-08-24
3 | Surveying the Spring landscape |  | 0.5 | 2020-08-24 | 2020-08-24
4 | What’s new in Spring |  | 1 | 2020-08-24 | 2020-08-24
5 | Declaring beans |  | 0.5 | 2020-08-24 | 2020-08-24
6 | Injecting into bean properties |  | 0.5 | 2020-08-24 | 2020-08-24
7 | Wiring with expressions |  | 0.5 | 2020-08-24 | 2020-08-24
8 | Automatically wiring bean properties |  | 0.5 | 2020-08-24 | 2020-08-24
9 | Wiring with annotations |  | 0.5 | 2020-08-24 | 2020-08-24
10 | Automatically discovering beans |  | 0.5 | 2020-08-24 | 2020-08-24 |  |  |  |  | 2019-11-10
11 | Using Spring’s Java-based configuration |  | 0.5 | 2020-08-24 | 2020-08-24
12 | What’s aspect-oriented programming |  | 1 | 2020-08-25 | 2020-08-25
13 | Selecting join points with pointcuts |  | 0.5 | 2020-08-25 | 2020-08-25
14 | Declaring aspects in XML |  | 1 | 2020-08-25 | 2020-08-25
15 | Annotating aspects |  | 1 | 2020-08-25 | 2020-08-25
16 | Injecting AspectJ aspects |  | 0.5 | 2020-08-25 | 2020-08-25
17 | Learning Spring’s data access philosophy |  | 1 | 2020-10-14 | 2020-10-14
18 | Configuring a data source |  | 1 | 2020-09-16 | 2020-09-16
19 | Using JDBC with Spring |  | 1 | 2020-09-16 | 2020-09-16
20 | Integrating Hibernate with Spring |  | 1 | 2020-09-25 | 2020-09-25
21 | Spring and the Java Persistence API |  | 1 | 2020-08-25 | 2020-08-25
22 | Understanding transactions |  | 0.5 | 2020-10-27 | 2020-10-27
23 | Choosing a transaction manager |  | 0.5 | 2020-10-27 | 2020-10-27
24 | Programming transactions in Spring |  | 0.5 | 2020-10-28 | 2020-10-28
25 | Declaring transactions |  | 0.5 | 2020-10-28 | 2020-10-28
26 | Getting started with Spring MVC |  | 1 | 2020-08-25 | 2020-08-25
27 | Writing a basic controller |  | 1 | 2020-08-25 | 2020-08-25
28 | Handling controller input |  | 2 | 2020-08-26 | 2020-08-26
29 | Processing forms |  | 2 | 2020-08-26 | 2020-08-26
30 | Handling file uploads |  | 1 | 2020-09-08 | 2020-09-08
31 | Installing Spring Web Flow |  | 1 | 2020-08-27 | 2020-08-27
32 | The components of a flow |  | 1 | 2020-08-27 | 2020-08-27
33 | Putting it all together: the pizza flow
34 | Securing web flows |  | 1 | 2020-08-27 | 2020-08-27
35 | Introducing Spring Security |  | 1 | 2020-08-27 | 2020-08-27
36 | Securing web requests |  | 1 | 2020-08-28 | 2020-08-28
37 | Securing view-level elements |  | 0.5 | 2020-08-28 | 2020-08-28
38 | Authenticating users |  | 1 | 2020-08-28 | 2020-08-28
39 | Securing methods |  | 1 | 2020-08-28 | 2020-08-28
40 | An overview of Spring remoting |  | 0.5 | 2020-08-28 | 2020-08-28
41 | Working with RMI |  | 1 | 2020-08-28 | 2020-08-28
42 | Exposing remote services with Hessian and Burlap
43 | Using Spring’s HttpInvoker
44 | Publishing and consuming web services |  | 1 | 2020-08-31 | 2020-08-31
45 | Getting REST |  | 1 | 2020-08-31 | 2020-08-31
46 | Writing resource-oriented controllers |  | 1 | 2020-08-31 | 2020-08-31
47 | Representing resources |  | 1 | 2020-08-31 | 2020-08-31
48 | Writing REST clients |  | 1 | 2020-08-31 | 2020-08-31
49 | Submitting RESTful forms |  | 1 | 2020-09-07 | 2020-09-07
50 | A brief introduction to JMS |  | 0.5 | 2020-09-04 | 2020-09-04
51 | Setting up a message broker in Spring |  | 0.5 | 2020-09-04 | 2020-09-04
52 | Using Spring’s JMS template |  | 0.5 | 2020-09-04 | 2020-09-04
53 | Creating message-driven POJOs |  | 0.5 | 2020-09-04 | 2020-09-04
54 | Using message-based RPC |  | 0.5 | 2020-10-29 | 2020-10-29
55 | Exporting Spring beans as MBeans
56 | Remoting MBeans
57 | Handling notifications
58 | Externalizing configuration
59 | Wiring JNDI objects
60 | Sending email
61 | Scheduling and background tasks

## SpringBoot
S.NO | Topic | Estimatted hours | week | start Date | end date | Doubts | comments | Note(If any)
1 | Getting Started | 1 |  | 2020-08-31 | 2020-08-31
2 | Developing Your First Spring Boot Application | 2 |  | 2020-09-01 | 2020-09-01
3 | Using Spring Boot | 1 |  | 2020-09-01 | 2020-09-01
4 | Spring Boot features | 1 |  | 9/1/2020 | 9/1/2020
5 | Externalized Configuration | 1 |  | 2020-09-02 | 2020-09-02
6 | Spring Profiles | 0.5 |  | 2020-09-02 | 2020-09-02
7 | Logging | 1 |  | 2020-09-02 | 2020-09-02
8 | Internationalization | 0.5 |  | 2020-09-02 | 2020-09-02
9 | JSON | 0.5 |  | 2020-09-02 | 2020-09-02
10 | Security | 1.5 |  | 2020-09-02 | 9/2/2020
11 | Working with SQL Databases | 2 |  | 2020-09-03 | 9/3/2020
12 | Working with NoSQL Technologies | 1 |  | 2020-09-03 | 9/3/2020
13 | Caching | 1 |  | 2020-09-03 | 2020-09-03
14 | Messaging | 1.5 |  | 2020-09-04 | 2020-09-04
15 | Validation | 0.5 |  | 2020-09-04 | 2020-09-04
16 | Distributed Transactions with JTA | 0.5 |  | 2020-09-10 | 2020-09-10
17 | Spring Integration | 0.5 |  | 2020-09-07 | 2020-09-07
18 | Testing | 1 |  | 2020-09-07 | 2020-09-07
19 | Spring Boot Actuator:Production-ready feature | 1 |  | 2020-09-07 | 2020-09-07
20 | Monitoring and Management over HTTP | 0.5 |  | 2020-09-07 | 2020-09-07

## MicroServices
S.NO | Topic | Hours | Week | Training Date | Actual Completion Time(in hours) | Question | Comments | Note(If any)
1 | Introduction to Microservices | 1 |  | 14/09/2020 | 1
2 | What is Microservices | 1 |  | 14/09/2020 | 1
3 | What is Spring and why is it relevant to microservices | 1 |  | 15/09/2020 | 1
4 | What is Cloud and cloud-based microservices | 1 |  | 15/09/2020 | 1
5 | Spring Boot | 1 |  | 15/09/2020 | 1
6 | Spring Cloud Config | 1 |  | 15/09/2020 | 1
7 | Spring Cloud service discovery | 1 |  | 15/09/2020 | 1
8 | Spring Cloud/Netflix Hystrix and Ribbon | 1 |  | 15/09/2020 | 1
9 | Spring Cloud/Netflix Zuul | 1 |  | 16/09/2020 | 1
10 | Spring Cloud Stream | 1 |  | 16/09/2020 | 1
11 | Spring Cloud Sleuth | 1 |  | 16/09/2020 | 1
12 | Spring Cloud Security | 1 |  | 16/09/2020 | 1
13 | Architecture | 1 |  | 16/09/2020 | 1
14 | Monolithic vs MicroServices Architecture | 1 |  | 15/09/2020 | 1
15 | Designing the microservice architecture | 1 |  | 17/09/2020 | 1
16 | When not to use microservices | 0.5 |  | 17/09/2020 | 0.5
17 | Config Server | 0.5 |  | 17/09/2020 | 0.5
18 | Building our Spring Cloud configuration server | 1 |  | 17/09/2020 | 1
19 | Integrating Spring Cloud Config with a Spring Boot client | 1 |  | 17/09/2020 | 1
20 | Protecting sensitive configuration information | 0.5 |  | 17/09/2020 | 0.5
21 | Service Discovery | 0.5 |  | 17/09/2020 | 0.5
22 | Architecture of service discovery | 0.5 |  | 17/09/2020 | 0.5
23 | Building your Spring Eureka Service | 1 |  | 18/09/2020 | 1
24 | Registering services with Spring Eureka | 1 |  | 18/09/2020 | 1
25 | Using service discovery to look up a service | 0.5 |  | 18/09/2020 | 0.5
26 | API Gateway | 0.5 |  | 18/09/2020 | 0.5
27 | What is a services gateway | 1 |  | 21/09/2020 | 1
28 | Introducing Spring Cloud and Netflix Zuul | 1 |  | 21/09/2020 | 1
29 | Configuring routes in Zuul | 1 |  | 21/09/2020 | 1
30 | Load Balancing | 1 |  | 22/09/2020 | 1
31 | Securing your microservices | 1 |  | 22/09/2020 | 1

## Hibernate
|  |  | Start Date | 22/09/2020
|  |  | End Date | 2020-05-10
S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | Actual Completion Time(in hours) | Reviewer Name | Review Comments | Note(If any)
1 | HIBERNATE – ORM |  | 22/09/2020 |  | 1 | 1
2 | HIBERNATE – OVERVIEW |  | 22/09/2020 |  | 1 | 1
3 | HIBERNATE – ARCHITECTURE |  | 23/09/2020 |  | 1 | 1
4 | HIBERNATE – ENVIRONMENT SETUP |  | 23/09/2020 |  | 0.5 | 0.5
5 | HIBERNATE – CONFIGURATION |  | 23/09/2020 |  | 0.5 | 0.5
6 | HIBERNATE – SESSIONS |  | 23/09/2020 |  | 1 | 1
7 | HIBERNATE – PERSISTENT CLASS |  | 24/09/2020 |  | 1 | 1
8 | HIBERNATE – MAPPING FILES |  | 24/09/2020 |  | 0.5 | 0.5
9 | HIBERNATE – MAPPING TYPES |  | 24/09/2020 |  | 0.5 | 0.5
10 | HIBERNATE – O/R MAPPINGS |  | 24/09/2020 |  | 1 | 1
11 | COLLECTION MAPPING |  | 24/09/2020 |  | 0.5 | 0.5
12 | SET MAPPINGS |  | 24/09/2020 |  | 0.5 | 0.5
13 | SORTED SET MAPPING |  | 25/09/2020 |  | 0.5 | 0.5
14 | LIST MAPPING |  | 25/09/2020 |  | 0.5 | 0.5
15 | BAG MAPPING |  | 25/09/2020 |  | 0.5 | 0.5
16 | MAP MAPPINGS |  | 25/09/2020 |  | 0.5 | 0.5
17 | SORTED MAP MAPPING |  | 25/09/2020 |  | 0.5 | 0.5
18 | ASSOCIATON MAPPING |  | 28/09/2020 |  | 1 | 1
19 | INHERITANCE MAPPING |  | 28/09/2020 |  | 1 | 1
20 | COMPONENT MAPPING |  | 28/09/2020 |  | 1 | 1
21 | HIBERNATE – ANNOTATIONS |  | 29/09/2020 |  | 1 | 1
22 | HIBERNATE – QUERY LANGUAGE |  | 29/09/2020 |  | 1 | 1
23 | HIBERNATE – CRITERIA QUERIES |  | 30/09/2020 |  | 1 | 1
24 | HIBERNATE – NATIVE SQ |  | 30/09/2020 |  | 1 | 1
25 | HIBERNATE – CACHING |  | 2020-01-10 |  | 1 | 1
26 | HIBERNATE – BATCH PROCESSING |  | 2020-01-10 |  | 1 | 1
27 | HIBERNATE – INTERCEPTORS |  | 2020-05-10 |  | 1 | 1

## Postgres
|  | Training Start Date | 2020-05-10
|  | Training End Date | 16/10/2020
S.NO | Topic | Duration | Start Date | End Date | Question | Comments | Note(If any)
1 | Getting Started with PostgreSQL | 1 | 2020-05-10
2 | Querying Data | 1 | 2020-05-10
3 | Filtering Data | 1.5 | 2020-06-10
4 | Joining Multiple Tables | 1.5 | 2020-06-10
5 | Grouping Data | 1 | 7/10/2020
6 | Performing Set Operations | 1 | 7/10/2020
7 | Grouping Sets | 1 | 7/10/2020
8 | Subquery | 1 | 8/10/2020
9 | Common Table Expressions | 1 | 8/10/2020
10 | Modifying Data | 1 | 8/10/2020
11 | Transactions | 1 | 9/10/2020
12 | Import & Export Data | 1 | 9/10/2020
13 | Managing Databases | 1 | 12/10/2020
14 | Managing Tables | 1 | 12/10/2020 |  |  |  |  | a
15 | Understanding PostgreSQL Constraints | 1 | 12/10/2020
16 | PostgreSQL Data Types in Depth | 1 | 13/10/2020
17 | Managing Schemas | 1 | 13/10/2020
18 | Conditional Expressions & Operators | 1 | 13/10/2020
19 | PostgreSQL Utilities | 1 | 14/10/2020
20 | PostgreSQL Recipes | 1 | 14/10/2020
21 | PostgreSQL Stored Procedures | 1.5 | 15/10/2020
22 | PostgreSQL Triggers | 1.5 | 15/10/2020
23 | PostgreSQL Views | 1.5 | 16/10/2020

## SQL
|  | Training Start Date | 19/10/2020
Training End Date
S.NO | Topic | Trainer Name | Training Date | Assessment Description | Estimated Completetion Time(in hours) | Actual Completion Time(in hours) | Reviewer Name | Review Comments | Note(If any)
1 | Introduction |  | 19/10/2020 |  | 1 | 1
2 | Relational Databases |  | 19/10/2020 |  | 0.5 | 0.5
3 | SQL Basics |  | 19/10/2020 |  | 0.5 | 0.5
4 | Simple Queries- SELECT, FROM, WHERE, GROUP BY, HAVING ORDER BY, DISTINCT, BETWEEN, IN, LIKE, AND, OR, NOT |  | 19/10/2020 |  | 1 | 1
5 | Multitable Queries (JOINS)- Simple Joins, Natural Joins, Non-Equi-joins, Self-Joins,Left Outer Join, Right Outer Join, Inner Join |  | 20/10/2020 |  | 1.5 | 1.5
6 | Summary Queries |  | 20/10/2020 |  | 1.5 | 1.5
7 | Subqueries and Query Expressions |  | 21/10/2020 |  | 1.5 | 1.5
8 | Database Updates |  | 21/10/2020 |  | 1 | 1
9 | Data Integrity |  | 21/10/2020 |  | 1 | 1
10 | Transaction Processing |  | 22/10/2020 |  | 1 | 1
11 | Creating a Database |  | 22/10/2020 |  | 1 | 1
12 | Views |  | 22/10/2020 |  | 1 | 1
13 | SQL Security |  | 23/10/2020 |  | 1 | 1
14 | The System Catalog |  | 23/10/2020 |  | 1 | 1
15 | Embedded SQL |  | 26/10/2020 |  | 1 | 1
16 | Dynamic SQL |  | 26/10/2020 |  | 1 | 1
17 | SQL APIs |  | 27/10/2020 |  | 1 | 1
18 | Database Processing and Stored Procedural SQL |  | 27/10/2020 |  | 1.5 | 1.5
19 | SQL and Data Warehousing |  | 28/10/2020 |  | 1 | 1
20 | SQL and Application Servers |  | 28/10/2020 |  | 1 | 1
21 | SQL Neworking and Distributed Databases |  | 29/10/2020 |  | 1 | 1
22 | SQL and Objects |  | 29/10/2020 |  | 1 | 1
23 | SQL and XML |  | 2020-02-11 |  | 1 | 1
24 | Specialty Databases |  | 2020-02-11 |  | 1 | 1
25 | The Future of SQL |  | 2020-02-11 |  | 1 | 1
Reference: SQL THE COMPLETE REFERENCE